## Hotel Reservation System
No | Task | Assignee | Assign |  | Actual |  | Progress | Status | Remark
|  |  | Start Date | End Date | Start Date | Start Date
1 | Reservation CRUD operation | May Phoo Wai | 2021-11-08 | 2021-11-10 | 2021-11-08
2 | Online Booking Admin | May Phoo Wai | 2021-11-11 | 2021-11-13
3 | Confirm Email | May Phoo Wai | 2021-11-14 | 2021-11-15
4 | Design | May Phoo Wai | 2021-11-16 | 2021-11-17
5 | Bind all page | Group3 | 2021-11-18 | 2021-11-19
6 | Hotel CRUD | Khin Aye Aye Nyein | 2021-11-08 | 2021-11-09
7 | Room CRUD | Khin Aye Aye Nyein | 2021-11-10 | 2021-11-13
8 | Search Reservation | Khin Aye Aye Nyein | 2021-11-14 | 2021-11-15
9 | Design | Khin Aye Aye Nyein | 2021-11-16 | 2021-11-17
10 | User CRUD | Zin MIn Htet Aung | 2021-11-08 | 2021-11-09
11 | Log in authorization | Zin MIn Htet Aung | 2021-11-10 | 2021-11-13
12 | Graph | Zin MIn Htet Aung | 2021-11-14 | 2021-11-15
13 | Design | Zin MIn Htet Aung | 2021-11-16 | 2021-11-17
14 | Home Page | Ei Thein Gi | 2021-11-08 | 2021-11-10
15 | Online Booking | Ei Thein Gi | 2021-11-11 | 2021-11-12
16 | Hotel User View | Ei Thein Gi | 2021-11-13 | 2021-11-14
17 | Room User View | Ei Thein Gi | 2021-11-14 | 2021-11-16
18 | Design | Ei Thein Gi | 2021-11-17 | 2021-11-17
19
20
21
22
23
24
25
26
27
28
29
30
31